**Support to UkraineInvest in the development of institutional capacity for attracting of FDI at the regional level: Ternopil oblast**

Objective: Integration of FDI in regional development strategy of Ternopil oblast till 2020, conducting of activities on its implementation

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **№ п/п** | **Activity / Period** |  | **01/05/2018-31/03/2019)** | **Experts** |
| 05-06/2018 | 07-09/18 | 10-12/18 | 01-03/19 |
| 1 | **Assessment of potential and investment needs, conducting of activities on attracting of target investors (ISTE + UI)** |
| 1.1. | Defining the sectors, which have the best investment potential  |  | **Х** |  |  |  | Dusan Kulka, Vasyl Fedyuk |
| 1.2 | Identification of target countries and companies (data base), which are optimal for the oblast | **Х** |  |  |  | Dusan Kulka, Vasyl Fedyuk |
| 1.3 | Development of campaigns / activities on attracting of target investors  | **Х** |  |  |  | Dusan Kulka |
| 1.4 | Support in implementation of campaign /activities on attracting target investors (UI) | **Х** | **Х** | **Х** |  | Ukraine Invest |
| 1.5 | Organisation of investment missions (UI) |  |  | **Х** | **Х** | Ukraine Invest |
| **2** | **Personnel Institutional capacity development (RDPA + STE)** |  |
| 2.1 | Development (actualization, adaptation) of training  |  | **Х** |  |  |  | Vasyl Fedyuk, Oksana Fedorovich, Dusan Kulka |
| 2.2 | Conduct of training  |  | **Х** |  |  | Vasyl Fedyuk, Oksana Fedorovich |
| 2.3 | Methodological support in introduction of standards for investors support and service  |  |  | **Х** | **Х** | Vasyl Fedyuk |
| 2.4 | Support for the ARD of Ternopil region (trainings, coaching) |  |  | **X** | **X** | **X** | Yuri Tretyak, Vasyl Fedyuk |
| 3 | **Support in creation of information and marketing tools (RDPA +STE)** |
| 3.1 | Support in the development of an investment passport of the oblast  |  | **X** |  |  |  | Vasyl Fedyuk |
| 3.2 | Support in development of investment web-portal  |  | **Х** | **X** |  |  | Vasyl Fedyuk, Oksana Fedorovich |
| 4 | **Assistance in the formation of investment products and infrastructure (ISTE + STE + UI)** |
| 4.1 | Methodological assistance in preparation of objects/investment sites (UI) |  | **Х** | **Х** | **Х** | **Х** | Ukraine Invest |
| 4.2 | Development of measures for the creation of investment infrastructure |  | **Х** |  |  |  | Dusan Kulka, Vasyl Fedyuk |
| 4.3 | Support for the concept of an industrial park |  |  | **Х** |  |  | Vasyl Fedyuk, Oksana Fedorovich |
| 5 | **Adaptation of labor resources for the needs of the regional market (RDPA: Rusanov, Kashevsky)** |
| 5.1 | Seminar/ round table  |  | **Х** |  |  |  | Gennadiy Rusanov |
| 5.2 | Package of recommendations to strengthen human resource capacity (based on research in Rivne and Lviv oblasts) |  |  | **Х** |  |  | Genadiy Rusanov, Vasyl Kashevski |